## Sheet1
Group 3 RACI
Topic
Task | DANIEL MALINSKY | GURUCHANDRA KUNDENA | BHAVYA K N | SREEVANI SIDDAREADYGARI | Timeline | Task Status | Task Done By
Overseeing entire project | C | R | I | I | 2024-04-18 | Done | GURUCHANDRA KUNDENA
Acting as liaison & Maintain RACI | R | C | I | I | 2024-04-18 | Done | DANIEL MALINSKY
Data Identification and collection | R | I | C | I | 2024-04-18 | Done | DANIEL MALINSKY
Data profilling | C | I | I | R | 2024-04-20 | Done | SREEVANI SIDDAREADYGARI
Data Modelling | C | I | R | I | 2024-04-20 | Done | BHAVYA K N
Conceptual modelling | I | R | C | I | 2024-04-20 | Done | GURUCHANDRA KUNDENA
IAM role configuration | I | I | R | C |  |  | GURUCHANDRA KUNDENA
Designing AWS Extraction | C | R | I | I | 2024-04-06 | Done | GURUCHANDRA KUNDENA
Setting up eventbridge | I | R | C | C |  |  | GURUCHANDRA KUNDENA
Setting up lambda functions | I | R | C | I | 2024-04-05 | Done | GURUCHANDRA KUNDENA
AWS Transform | C | I | R | I | 2024-04-14 | Done | BHAVYA K N
AWS Load | I | I | R | I | 2024-04-14 | Done | BHAVYA K N
Physical Layout | I | I | R | C | 2024-04-14 | Done | BHAVYA K N
ER Diagram | I | I | I | R | 2024-04-18 | Done | SREEVANI SIDDAREADYGARI
Managing data transformation | C | R | I | I | 2024-04-07 | Done | GURUCHANDRA KUNDENA
Managing data loading | C | R | I | I | 2024-04-18 | Done | GURUCHANDRA KUNDENA
Collaborating with database architect for data warehousing | I | I | I | R | 2024-04-25 | Done | SREEVANI SIDDAREADYGARI
Designing data warehouse schema | C | I | I | R | 2024-04-27 | Done | SREEVANI SIDDAREADYGARI
Visualization using Tableau | I | C | R | I | 2024-05-05 | Done | BHAVYA K N
Reporting & Presentation | I | I | R | C | 2024-05-05 | Done | BHAVYA K N
Detailed Discription
DANIEL MALINSKY | Acting as liaison & Maintain RACI, Data Identification and collection
GURUCHANDRA KUNDENA | collaborating with db architect for data warehousing
BHAVYA K N | Project manage,Data Modelling,Conceptual modelling, aws transform, aws load, managing data transform
SREEVANI SIDDAREADYGARI | data profiling ,Physical layout, ER diagram ,Managing data loading , Reporting and presentation , designing data warehouse